## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Enter ticket description | Must Have | None | Zeba | Done
Sprint 1 | Sprint 1 | US-02 | Preprocess user input | Must Have | US-01 | Zeba | Done
Sprint 1 | Sprint 1 | US-03 | Categorize tickets using AI | Must Have | US-02 | Zeba | Done
Sprint 1 | Sprint 1 | US-04 | Auto-assign priority | Must Have | US-03 | Zeba | Done
Sprint 2 | Sprint 2 | US-05 | Persist tickets in database | Must Have | US-04 | Zeba | Done
Sprint 2 | Sprint 2 | US-06 | Display all tickets | Should Have | US-05 | Zeba | Done
Sprint 3 | Sprint 3 | US-07 | Update ticket status | Should Have | US-06 | Zeba | Done
Sprint 3 | Sprint 3 | US-08 | Close resolved tickets | Could Have | US-07 | Zeba | Done

## Sprint Backlog
NOTES:Task size should be between 0.5 to 12 hours
US ID | Task ID | Task Descriptions | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort(In hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Collect and analyze historical ticket dataset | 2025-11-27 | 2025-11-29 | Zeba | Design | Done | 4 | bar: Day 1 to Day 3
US-02 | T-02 | Clean and preprocess ticket text data | 2025-11-30 | 2025-12-03 | Zeba | Coding | Done | 5 | bar: Day 2 to Day 4
US-03 | T-03 | Train ML model for ticket classification | 2025-12-04 | 2025-12-08 | Zeba | Build | Done | 8 | bar: Day 3 to Day 6
US-04 | T-04 | Implement Named Entity Recognition (NER) | 2025-12-09 | 2025-12-11 | Zeba | Coding | Done | 6 | bar: Day 4 to Day 6
US-05 | T-05 | Predict ticket category and priority | 2025-12-12 | 2025-12-15 | Zeba | Build | Done | 7 | bar: Day 5 to Day 8
SPRINT 2 BACKLOG
US-06 | T-06 | Develop ticket creation engine (structured output) | 2025-12-16 | 2025-12-20 | Zeba | Coding | Done | 6 | bar: Day 7 to Day 9
US-07 | T-07 | Store generated tickets in SQLite database | 2025-12-21 | 2025-12-26 | Zeba | Build | Done | 5 | bar: Day 8 to Day 9
US-08 | T-08 | Implement ticket status workflow | 2025-12-27 | 2025-12-29 | Zeba | Build | Done | 4 | bar: Day 9 to Day 10
SPRINT 3 BACKLOG
US-09 | T-09 | Design and implement Streamlit UI | 2026-01-06 | 2026-01-10 | Zeba | Design | Done | 6 | bar: Day 8 to Day 10
US-10 | T-10 | Integrate UI with AI and database | 2026-01-11 | 2026-01-13 | Zeba | Integration Test | Done | 4 | bar: Day 10 to Day 11
US-11 | T-11 | Perform system testing | 2026-01-14 | 2026-01-16 | Zeba | System Test | Done | 3 | bar: Day 11 to Day 13
US-12 | T-12 | Regression testing and final validation | 2026-01-17 | 2026-01-18 | Zeba | Regression Test | Done | 2 | bar: Day 13 to Day 14

## Stand Up Meeting
Sprint | Day | Impediments | Actions Taken
Sprint 1 | Day 2 | Dataset contained inconsistent and incomplete ticket descriptions | Cleaned data and removed noisy records
Sprint 1 | Day 4 | Text preprocessing reduced important keywords | Adjusted stop-word list and preprocessing rules
Sprint 1 | Day 6 | Low accuracy in ticket category prediction | Tuned TF-IDF parameters and retrained model
Sprint 1 | Day 9 | Named Entity Recognition missing some entities | Improved NER patterns and re-evaluated data
Sprint 1 | Day 11 | Priority prediction inconsistent for urgent tickets | Added rule-based priority override logic
Sprint 2 | Day 2 | Difficulty in mapping predictions to ticket structure | Redesigned ticket creation logic
Sprint 2 | Day 5 | Tickets were not persisting after refresh | Integrated SQLite database storage
Sprint 2 | Day 8 | Ticket status updates not reflected correctly | Fixed backend update workflow
Sprint 3 | Day 3 | UI delays during ticket submission | Optimized Streamlit state handling
Sprint 3 | Day 6 | UI and backend integration issues | Performed integration testing and bug fixes
Sprint 3 | Day 9 | Minor functional bugs during testing | Conducted system testing and fixes
Sprint 3 | Day 12 | Edge-case failures found in regression testing | Fixed issues and revalidated the system

## Retrospection
SL# | Sprint # | Sprint start date | Sprint end date | Team member name | Start doing | Stop Doing | Continue Doing | Action Doing
1 | Sprint 1 | 2025-11-27 | 2025-12-10 | Zeba | Early dataset analysis before model training | Using raw uncleaned text for experiments | Step-by-step ML development | Improved preprocessing pipeline
2 | Sprint 1 | 2025-11-27 | 2025-12-10 | Zeba | Validating dataset quality | Training models without evaluation | Parameter tuning | Parameter tuning
3 | Sprint 2 | 2025-12-16 | 2025-12-29 | Zeba | Designing ticket creation logic clearly | Temporary in-memory storage | Modular backend coding | Implemented SQLite persistence
4 | Sprint 2 | 2025-12-16 | 2025-12-29 | Zeba | Defining ticket status workflow | Hard-coded status values | Clean logic separation | Implemented Open–In Progress–Closed workflow
5 | Sprint 3 | 2026-01-06 | 2026-01-18 | Zeba | UI development after backend stability | Parallel UI and backend changes | Incremental integration | Streamlit UI finalized
6 | Sprint 3 | 2026-01-06 | 2026-01-18 | Zeba | System and regression testing | Feature additions late in sprint | Bug fixing | Stability improvements
7 | Sprint 3 | 2026-01-06 | 2026-01-18 | Zeba | Proper documentation | Last-minute documentation | Code comments | Project finalized and reviewed